## Sheet1
Product Backlog & User Story
ID | Epic | As a … | I Want to … | So that … | Tasks | Priority | Estimation
101 | User Authentication | User | log in to the app | I can access my personal dashboard | Design login UI | HIGH | 3
Coding
102 | User Registration | User | create a new account | I can join and vote in polls | Design sign up UI | HIGH | 3
103 | Navigation | User | navigate between pages | I can access different features | Bottom navigation setup | HIGH | 2
104 | Homepage | User | view trending polls | I can vote on popular topics | Build homepage UI | HIGH | 5
105 | Poll Component | User | view poll cards | I can read poll information | Create PollCard widget | MEDIUM | 2
106 | Saved Polls | User | see saved polls | I can revisit them | Build saved polls page | MEDIUM | 3
107 | Search Feature | User | search for polls | I can find specific polls easily | Design search page | MEDIUM | 4
108 | Reusable Widgets | Developer | build reusable component | UI looks consistent | Create CategoryIcon, SavedItem | LOW | 2
109 | Profile Page | User | view my profile | I can see my information | Build profile UI | MEDIUM | 3
110 | Settings Page | User | adjust settings | I can customize my experience | Build settings UI | MEDIUM | 3
111 | Logout Feature | User | log out from the app | I can secure my account | Implement logout | HIGH | 2
112 | Dark Mode | User | enable dark mode | I can use the app comfortably at night | Implement dark mode toggle | MEDIUM | 3
113 | View Result | User | view voting results | I can see poll outcomes | Build result page | HIGH | 4
114 | Share Feature | User | share poll results | I can share with friends | Implement share button | MEDIUM | 2
115 | Feedback Feature | User | give feedback on polls | I can express my opinion | Build feedback form | MEDIUM | 3
116 | Edit Profile | User | edit my profile information | I can update my data anytime | Build edit profile UI & logic | MEDIUM | 3
117 | Account Linking | User | link my email and social media | I can log in easily | Implement linking feature | MEDIUM | 4
118 | Report Problem | User | report app problems | Developer can fix bugs quickly | Build report problem form | HIGH | 2
Sprint Planning |  | Sprint Planning |  | Sprint Planning |  | Sprint Planning
Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Goals : |  | Sprint Goals : |  | Sprint Goals : |  | Sprint Goals :
1 | Implement authentication and navigation | 1 | Develop main pages and components | 1 | Develop profile and settings pages | 1 | Implement view result and share features
2 | Setup user registration and login flow | 2 | Implement search and saved polls features | 2 | Implement logout, dark mode, and feedback features | 2 | Implement edit profile, account linking, and report problem
Sprint Backlog : |  | Sprint Backlog : |  | Sprint Backlog : |  | Sprint Backlog :
ID | Backlog Items | ID | Backlog Items | ID | Backlog Items | ID | Backlog Items
101 | As a user, I want to log in so I can access my personal dashboard | 104 | As a user, I want to see trending polls so I can vote on popular topics | 109 | As a user, I want to view my profile so I can see my information | 113 | As a user, I want to view voting results so I can see poll outcomes
102 | As a user, I want to create a new account so I can join and vote in polls | 106 | As a user, I want to see saved polls so I can revisit them | 110 | As a user, I want to adjust settings so I can customize my experience | 114 | As a user, I want to share poll results so I can share with friends
103 | As a user, I want to navigate between pages so I can explore the app easily | 107 | As a user, I want to search for polls so I can find specific topics easily | 111 | As a user, I want to log out from the app so I can secure my account | 116 | As a user, I want to edit my profile information so I can update my data anytime
|  |  |  | 112 | As a user, I want to enable dark mode so I can use the app comfortably at night | 117 | As a user, I want to link my email and social media so I can log in easily
|  |  |  | 115 | As a user, I want to give feedback on polls so I can express my opinion | 118 | As a user, I want to report app problems so developer can fix bugs quickly
Daily Scrum Meeting Report | [5 empty] | 1 SPRINT MINIMAL 1 DAILY SCRUM MEETING REPORT
No. | Nama Anggota | Task yang dikerjakan | Tanggal Pengerjaan | Kendala yang dihadapi | Waktu Perkiraan Selesai
1 | Asyifa | Membuat UI login | 2005-06-01 | Error routing page | 1 hari
2 | Richi | Membuat homepage UI | 2005-06-02 | Layout overlapping | 2 hari
3 | Ahmad Danu | Membuat saved polls page | 2005-06-02 | Masalah provider state | 2 hari
4 | Sherly | Implementasi dark mode | 2005-06-03 | Error switch theme | 1 hari
5 | Derry | Membuat profile page UI | 03/06/2005 | Masalah integrasi data user | 2 hari
6 | Asyifa | Membuat setting page | 2005-06-01 | Tidak ada | 1 hari
7 | Ahmad Danu | Implementasi view result dan share | 2005-06-04 | Error parsing data | 2 hari
8 | Sherly | Membuat edit profile dan report problem page | 2005-06-04 | Belum connect API edit profile | 2 hari
Sprint Review |  |  | Sprint Review |  |  | Sprint Review |  |  | Sprint Review
Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4
Completed Task | Incompleted Task | What's Next | Completed Task | Incompleted Task | What's Next | Completed Task | Incompleted Task | What's Next | Completed Task | Incompleted Task | What's Next
Login page UI, settings page | Tidak ada | Develop homepage and saved polls | Homepage, saved polls | Tidak ada | Profile, settings, logout, dark mode, feedback | Profile, settings, logout, dark mode, feedback | Tidak ada | View result, share, edit profile, account linking, report problem | View result, share, edit profile, report problem | Account linking | Integrasi OAuth dan final testing
Sprint Retrospective |  |  |  |  | 1 SPRINT WAJIB ADA 1 SPRINT RETROSPECTIVE
Sprint 1
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Login dan settings page selesai cepat | Koordinasi task awal | Menunda standup meeting | Komunikasi yang baik via WA | Membuat backlog lebih detail
Sprint Retrospective
Sprint 2
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
UI sesuai desain | Testing unit belum dibuat | Coding tanpa testing | Desain UI sesuai Figma | Menulis unit test
Sprint Retrospective
Sprint 3
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Fitur selesai sesuai sprint goal | Masih ada bug kecil | Push langsung ke main branch | Daily standup tepat waktu | Gunakan branch develop untuk fitur baru
Sprint Retrospective
Sprint 4
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Kolaborasi berjalan baik | OAuth setup belum selesai | Mengabaikan testing di local | Komunikasi terbuka antar anggota | Fokus finishing account linking